## Timeline
No | Phase | Activity | Days/hr | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Delay | Owners | Status | Remarks/Comments
Phase 1 : X Week Purpose : Functional and NFR understanding, Scope freeze, Scripting
1 | Planning | Functional understanding, Functionality Walkthrough and Test Scenario freeze | [7 empty] | InProgress
2 | Planning | NFR details gathering and Open Points clarification | [7 empty] | Yet to Start
3 | Planning | Basis or Server configuration details and JVM enabling (if required), Monitoring tool setup | [7 empty] | Yet to Start
4 | Planning | Performance tool selection and setup Backend setup, monitoring tool setup (if required)
5 | Planning | Performance testing Environment Set up and readiness (production copy) | [7 empty] | Yet to Start
6 | Testscript | Performance Test Script creation for predefined Test scenarios and fine tuning the Test script | [7 empty] | Yet to Start
7 | Testscript | Performance Test Script Sanity run in Performance testing Environment and result collection | [7 empty] | Yet to Start
8 | Planning | Sign-off on User and task volume figures and Run time user/volume scenarios | [7 empty] | Yet to Start
9 | Testscript | Test data loading into test scripts and Backend setup for the Test data | [7 empty] | Yet to Start
10 | Execution | Performance Test Execution, see phase 2 for details
Phase 2 : X Week(DD.MM.YYYY to DD.MM.YYYY) Purpose : Initial load and Volume test with Production code in Performance environment(Note* Load/Volume will be changed according to the System behaviour in each Iteration)
Note* Load/Volume will be changed according to the System behaviour in each/Previous Iteration.
1 | Execution | Iteration1 : App Login: X numbers Fetch student and exam: Save marks requests: Y count Get Saved Scan: Y count Result Collection | [6 empty] | Santhosh | Yet to start
2 | Analysis | Gathering Raw results, Result comparing and Publishing with below details CPU Memory Response time System Availability (error like 503,500 are captured if occured during test) | [6 empty] | Santhosh | Yet to start

## PT Scenarios
Sl/no | Test Scenarios | Priority | User type |  |  | User count | Additional Comments
1 | School Login: (POST)
2 | Fetch student and exam (POST)
3 | Save marks (PUT)
4 | Get Saved Scan (POST)
sl/no | User/API Statistics for Performance test | Count/Peak hour | Count/Peak Day | per school | Dev envt | QA Comment | Clients Comments
1 | Total number of users/Teachers login in a day |  |  | 4
2 | Total number of fetch student exam requests for Class 1 to 3
3 | Total number of fetch student exam requests for Class 4 to 9
4 | Total number of Class 1 to 3 Students record that need to be sent in ONE Save Marks Request |  |  |  |  | Depends on the Class 1 to3 and class 4 to 9 count
5 | Total number of Class 4 to 9 Students record that need to be sent in ONE Save Marks Request
6 | Total number of Students record that need to be sent in ONE Save Marks Request
7 | Total number of Save Marks API request to sent to back-end | no. of schools*average no. of classes* |  |  |  | is equal to==>number of users logged in * iterations while running the test
8 | Total number of students data that is sent to back-end from Save Marks Request(Depends on above 3 requirements)
9 | Total number of Get Saved scan API requests | no. of schools*average no. of classes* |  |  |  | is equal to==>number of users logged in * iterations while running the test
10 | Duration of test |  |  |  |  | TBD
11 | Peak hour users in the System
12

## PT results
ITERATION 1 15/03/2023 Dry run Dev server Results | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec |  | App Web DataBase | Rendering | Memory CPU
School Login
Fetch student and exam
Save marks
Get Saved Scan
TOTAL
Dev server Dry run
ITERATION 1/15/03/2023 Dry run local server Results | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec |  | App Web DataBase | Rendering | Memory CPU
ITERATION 1/15/03/2023 Dry run local server Results | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec |  | App Web DataBase | Rendering | Memory CPU
01_App_Login
02_Fetch_Exam
03_Save_All
04_Get Saved Scan (POST)
Total Transcation

## Dev test results
ITERATION 1 15/03/2023 Dry run Dev server Results | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec |  | App Web DataBase | Rendering | Memory CPU
School Login | 10 | 2241 | 1361 | 4407 | 4407 | 4469 | 1294 | 4469 | 0% | 2.1777 | 2.85 | 0.87
Fetch student and exam | 10 | 1335 | 823 | 2870 | 2870 | 3898 | 729 | 3898 | 0% | 2.5176 | 54 | 1.33
Save marks | 10 | 359 | 356 | 378 | 378 | 378 | 341 | 378 | 0% | 3.0619 | 7.37 | 16.51
Get Saved Scan | 10 | 370 | 363 | 384 | 384 | 412 | 354 | 412 | 0% | 3.06 | 7.37 | 1.35
TOTAL | 50 | 861 | 374 | 1411 | 3898 | 4469 | 0 | 4469 | 0% | 8.0788 | 45.33 | 10.92
Dev server Dry run
1 user, 10 iterations, each user SAVE_All 1 student record and Get_Saved 10 student records
ITERATION 1/15/03/2023 Dry run local server Results | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec |  | App Web DataBase | Rendering | Memory CPU
School Login | 10 | 137 | 61 | 283 | 283 | 312 | 44 | 312 | 0% | 9.4697 | 12.38 | 3.67 | Local (4 Cores, 16 GB RAM, OS=Windows)
Debug Sampler | 10 | 0 | 1 | 1 | 1 | 2 | 0 | 2 | 0% | 14.3267 | 6.93 | 0
Fetch student and exam | 10 | 601 | 518 | 769 | 769 | 775 | 462 | 775 | 0% | 8.2645 | 177.26 | 4.29
Save marks | 10 | 104 | 62 | 175 | 175 | 188 | 22 | 188 | 0% | 12.3153 | 29.5 | 66.28
Get Saved Scan | 10 | 101 | 64 | 163 | 163 | 177 | 34 | 177 | 0% | 15.0376 | 36.02 | 6.46
TOTAL | 50 | 188 | 64 | 518 | 718 | 775 | 0 | 775 | 0% | 29.1375 | 163.35 | 39.15
ITERATION 30/03/2023 Dry run local server Results BEFORE Apurva's index change | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase | Rendering | Memory CPU
School Login | 100 | 3148 | 2064 | 5661 | 9723 | 12864 | 44 | 14541 | 0% | 2.2529 | 3.14 | 0.89
Fetch student and exam | 100 | 8855 | 7762 | 14845 | 17496 | 21015 | 439 | 24476 | 0% | 1.4545 | 1.94 | 0.76
Save marks Class1to3 | 100 | 6824 | 7143 | 10638 | 11154 | 11789 | 675 | 13416 | 0% | 1.3436 | 107.76 | 259.2
Save marks Class4to8 | 100 | 8609 | 9540 | 11533 | 12401 | 12863 | 1615 | 12864 | 0% | 1.2965 | 1574.04 | 1865.77
Get Saved Scan Class1to3 | 100 | 4580 | 4456 | 7480 | 7662 | 8403 | 692 | 8419 | 0% | 1.3122 | 78.31 | 0.57
Get Saved Scan Class4to8 | 100 | 3835 | 3591 | 6466 | 7021 | 8829 | 631 | 9086 | 0% | 1.3219 | 932.4 | 0.57
Total | 600 | 5975 | 5759 | 9437 | 10909 | 12627 | 682 | 13800 | 0% | 1.5 | 450 | 354
Test Duration 1:19 min Total 50 Users login on 2 Iterations (100 requests per each samples) Total 10,000 students records are Saved
ITERATION 30/03/2023 Dry run local server Results AFTER Apurva's index change (1st TEST RUN) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) | Rendering | Memory CPU
School Login | 100 | 2797 | 955 | 7763 | 9859 | 14144 | 528 | 15202 | 0% | 2.017 | 2.81 | 0.8
Fetch student and exam | 100 | 8696 | 6546 | 17392 | 21766 | 28146 | 1448 | 28563 | 0% | 1.2962 | 1.71 | 0.68
Save marks Class1to3 | 100 | 8919 | 9193 | 13218 | 14246 | 15424 | 1471 | 15581 | 0% | 1.2015 | 77.93 | 231.79
Save marks Class4to8 | 100 | 10997 | 11382 | 13985 | 14673 | 16188 | 4190 | 16735 | 0% | 1.1643 | 1188.49 | 1675.52
Get Saved Scan Class1to3 | 100 | 6065 | 6302 | 8664 | 8922 | 10204 | 1274 | 11073 | 0% | 1.2265 | 69.94 | 0.53
Get Saved Scan Class4to8 | 100 | 4826 | 4960 | 8297 | 8899 | 8989 | 493 | 10926 | 0% | 1.2997 | 1030.35 | 0.56
Total | 600 | 7050 | 6556 | 11553 | 13060 | 15515 | 1567 | 16346 | 0% | 1.36 | 395 | 318
Test Duration 1:26 min Total 50 Users login on 2 Iterations (100 requests per each samples) Total 10,000 students records are Saved
ITERATION 30/03/2023 Dry run local server Results AFTER Apurva's index change (2nd TEST RUN) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) | Rendering | Memory CPU
School Login | 100 | 5503 | 2230 | 11586 | 13099 | 19276 | 606 | 21111 | 0% | 0.97598 | 1.36 | 0.39
Fetch student and exam | 100 | 12714 | 12257 | 22637 | 24108 | 48651 | 702 | 52418 | 0% | 0.65512 | 0.85 | 0.34
Save marks Class1to3 | 100 | 20676 | 21275 | 28904 | 29784 | 32505 | 2911 | 35076 | 3% | 0.59632 | 38.96 | 111.59
Save marks Class4to8 | 100 | 27677 | 29017 | 33630 | 35586 | 37454 | 8752 | 38289 | 0% | 0.59973 | 605.33 | 863.04
Get Saved Scan Class1to3 | 100 | 12997 | 12314 | 20600 | 22533 | 23553 | 2321 | 24601 | 4% | 0.66534 | 38.63 | 0.28
Get Saved Scan Class4to8 | 100 | 8981 | 7938 | 15846 | 19349 | 22696 | 1210 | 24919 | 1% | 0.74334 | 524.2 | 0.32
Total | 600 | 14758 | 14171 | 22200 | 24076 | 30689 | 2750 | 32735 | 2% | 0.73 | 201 | 162
Test Duration 3:05 min Total 50 Users login on 2 Iterations (100 requests per each samples) Total 10,000 students records are Saved
ITERATION 30/03/2023 Dry run local server Results AFTER Apurva's index change (3rd TEST RUN) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) | Rendering | Memory CPU
School Login | 100 | 6777 | 3464 | 16413 | 25084 | 30556 | 141 | 31260 | 0% | 0.94863 | 1.32 | 0.38
Fetch student and exam | 100 | 19933 | 18125 | 36446 | 40079 | 46431 | 920 | 50155 | 0% | 0.6592 | 0.85 | 0.35
Save marks Class1to3 | 100 | 16025 | 18606 | 24013 | 25199 | 28461 | 2606 | 29098 | 0% | 0.58513 | 39.23 | 112.88
Save marks Class4to8 | 100 | 20633 | 21942 | 26307 | 28432 | 30903 | 3756 | 32186 | 0% | 0.55935 | 707.37 | 804.95
Get Saved Scan Class1to3 | 100 | 11948 | 12029 | 17671 | 18445 | 19565 | 3367 | 20545 | 0% | 0.55927 | 33.54 | 0.24
Get Saved Scan Class4to8 | 100 | 10400 | 8896 | 17781 | 19837 | 22886 | 2608 | 25912 | 0% | 0.56119 | 424.52 | 0.24
Total | 600 | 14286 | 13843 | 23010 | 26179 | 29800 | 2233 | 31340 | 0% | 0.63 | 201 | 153
Test Duration 3:05 min Total 50 Users login on 2 Iterations (100 requests per each samples) Total 10,000 students records are Saved
ITERATION 30/03/2023 Dry run local server Results BEFORE Apurva's index change (4th TEST RUN)-- 10 USERS | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) | Rendering | Memory CPU
School Login | 10 | 462 | 421 | 630 | 630 | 727 | 98 | 727 | 0% | 4.1357 | 5.76 | 1.64
Fetch student and exam | 10 | 1904 | 1751 | 2911 | 2911 | 4617 | 54 | 4617 | 0% | 1.471 | 1.92 | 0.77
Save marks Class1to3 | 10 | 1179 | 1126 | 1504 | 1504 | 2131 | 432 | 2131 | 0% | 1.2124 | 118.38 | 233.89
Save marks Class4to8 | 10 | 1795 | 1477 | 2538 | 2538 | 2554 | 744 | 2554 | 0% | 1.0934 | 1613.53 | 1573.43
Get Saved Scan Class1to3 | 10 | 927 | 1020 | 1084 | 1084 | 1715 | 287 | 1715 | 0% | 1.15 | 77.09 | 0.5
Get Saved Scan Class4to8 | 10 | 970 | 822 | 1602 | 1602 | 1789 | 199 | 1789 | 0% | 1.1619 | 1189.05 | 0.5
Total | 60 | 1206 | 1102 | 1711 | 1711 | 2255 | 302 | 2255 | 0% | 1.75 | 500 | 301
Test Duration 00:10 min Total 10 Users login on 1 Iteration (100 requests per each samples) Total 1,000 students records are Saved
ITERATION 30/03/2023 Dry run local server Results AFTER Apurva's index change (4th TEST RUN)-- 10 USERS | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | App Web DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) | Rendering | Memory CPU
School Login | 10 | 997 | 947 | 1710 | 1710 | 1815 | 63 | 1815 | 0% | 3.811 | 5.3 | 1.51
Fetch student and exam | 10 | 2409 | 2444 | 3066 | 3066 | 5502 | 19 | 5502 | 0% | 1.2385 | 1.71 | 0.65
Save marks Class1to3 | 10 | 2878 | 3267 | 4130 | 4130 | 5544 | 481 | 5544 | 0% | 0.73535 | 61.1 | 141.86
Save marks Class4to8 | 10 | 4685 | 5034 | 6114 | 6114 | 6231 | 1737 | 6231 | 0% | 0.57557 | 925.19 | 828.28
Get Saved Scan Class1to3 | 10 | 2323 | 2406 | 3784 | 3784 | 3936 | 295 | 3936 | 0% | 0.60096 | 41.06 | 0.26
Get Saved Scan Class4to8 | 10 | 1991 | 1273 | 4006 | 4006 | 5118 | 338 | 5118 | 0% | 0.5676 | 817.76 | 0.25
Total | 60 | 2547 | 2561 | 3801 | 3801 | 4691 | 488 | 4691 | 0% | 1.25 | 308 | 162
Test Duration 00:10 min Total 10 Users login on 1 Iteration (100 requests per each samples) Total 1,000 students records are Saved

## Indexing Results
ITERATION 04/03/2023 Local server Results BEFORE Index changes -- 30 USERS(v1_develop branch) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes |  |  | Please go through this link to understand the report https://jmeter.apache.org/usermanual/component_reference.html#Aggregate_Report
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) |  | Rendering | Memory CPU
School Login | 30 | 2698 | 3206 | 4026 | 4098 | 4160 | 431 | 4160 | 0% | 5.0192 | 6.78 | 1.95 | Performance test executed with below load a. Users logged in: 30, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 (Save Marks 1 to3 and Save marks 4 to 8) d. Total Save marks API calls:60 e. Students record saved per iteration:100 f. Total students record saved:3000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000
Fetch student and exam | 30 | 22937 | 15380 | 56131 | 57832 | 59351 | 11570 | 59351 | 0% | 0.46209 | 3.62 | 0.24
Get Roi | 30 | 3852 | 1651 | 10457 | 11407 | 16797 | 351 | 16797 | 0% | 0.57845 | 24.78 | 0.21
Get brand | 30 | 5106 | 2422 | 11961 | 13225 | 13748 | 411 | 13748 | 0% | 0.56037 | 6.89 | 0.21
Default brand | 30 | 1971 | 1815 | 4075 | 4362 | 5106 | 105 | 5106 | 0% | 0.5563 | 6.84 | 0.21
Save marks Class1to3 | 30 | 7514 | 7468 | 12924 | 13040 | 13661 | 1348 | 13661 | 0% | 0.52667 | 70.73 | 101.55
Save marks Class4to8 | 30 | 9033 | 10461 | 13541 | 14836 | 16845 | 1317 | 16845 | 0% | 0.55262 | 719.47 | 795.24
Get Saved Scan Class1to3 | 30 | 4400 | 4132 | 8189 | 8332 | 9248 | 60 | 9248 | 0% | 0.72314 | 12.96 | 0.31
Get Saved Scan Class4to8 | 30 | 3909 | 3688 | 7352 | 7406 | 8638 | 56 | 8638 | 0% | 0.88569 | 338.3 | 0.38
ITERATION 04/03/2023 Local server Results AFTER Index changes -- 30 USERS(index_branch_SS-184) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes | Percentage change for 30 users
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) Indexing done to below API calls School Login Fetch student and exam Get Roi Get brand Default brand Renaming to standard collection names and Connection pooling changes | Rendering | Memory CPU |  | Thread Group:School Login | 81%
School Login | 30 | 505 | 548 | 881 | 907 | 966 | 37 | 966 | 0% | 12.8977 | 20.57 | 5.02 | Performance test executed with below load a. Users logged in: 30, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 d. Total Save marks API calls:60 e. Students record saved per iteration:100 f. Total students record saved:3000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000 |  |  |  |  | Thread Group:Fetch student and exam | 66%
Fetch student and exam | 30 | 7668 | 6006 | 15362 | 15863 | 20012 | 324 | 20012 | 0% | 1.3768 | 9.88 | 0.72 | [5 empty] | Thread Group:Get Roi | 41%
Get Roi | 30 | 2261 | 2710 | 3994 | 4245 | 4843 | 60 | 4843 | 0% | 1.196 | 51.24 | 0.44 | [5 empty] | Thread Group:Get brand | 64%
Get brand | 30 | 1805 | 2299 | 3116 | 3120 | 3467 | 26 | 3467 | 0% | 1.0674 | 13.32 | 0.39 | [5 empty] | Thread Group:Default brand | 71%
Default brand | 30 | 568 | 598 | 1005 | 1061 | 1453 | 15 | 1453 | 0% | 1.0546 | 12.97 | 0.4
Save marks Class1to3 | 30 | 2064 | 2345 | 3131 | 3185 | 3654 | 353 | 3654 | 0% | 1.0021 | 132.86 | 193.22
Save marks Class4to8 | 30 | 2501 | 2750 | 3332 | 3413 | 3975 | 693 | 3975 | 0% | 0.97991 | 1176.11 | 1410.13
Get Saved Scan Class1to3 | 30 | 1474 | 1627 | 2232 | 2435 | 2828 | 73 | 2828 | 0% | 1.0034 | 54.11 | 0.43
Get Saved Scan Class4to8 | 30 | 1451 | 1600 | 2329 | 2402 | 2975 | 33 | 2975 | 0% | 1.0132 | 510.76 | 0.44
ITERATION 04/03/2023 Local server Results BEFORE Index changes -- 40 USERS(v1_develop branch) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) |  | Rendering | Memory CPU
School Login | 40 | 3636 | 3637 | 5823 | 6044 | 6118 | 775 | 6118 | 0% | 4.9863 | 6.74 | 1.94 | Performance test executed with below load a. Users logged in: 40, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 d. Total Save marks API calls:80 e. Students record saved per iteration:100 f. Total students record saved:4000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000
Fetch student and exam | 40 | 28190 | 19997 | 57362 | 59341 | 63876 | 15386 | 63876 | 0% | 0.57446 | 4.64 | 0.3
Get Roi | 40 | 8645 | 5961 | 18270 | 20379 | 23488 | 404 | 23488 | 0% | 0.60155 | 25.77 | 0.22
Get brand | 40 | 8930 | 9790 | 14872 | 19757 | 21328 | 323 | 21328 | 0% | 0.52005 | 6.39 | 0.19
Default brand | 40 | 2895 | 2592 | 5481 | 5789 | 6628 | 81 | 6628 | 0% | 0.49814 | 6.12 | 0.19
Save marks Class1to3 | 40 | 10614 | 10849 | 15012 | 18334 | 19264 | 2805 | 19264 | 2.5% | 0.43037 | 42.76 | 80.91
Save marks Class4to8 | 40 | 13403 | 12530 | 17728 | 18728 | 20160 | 7622 | 20160 | 0% | 0.40717 | 488.26 | 585.93
Get Saved Scan Class1to3 | 40 | 7191 | 6990 | 11148 | 12416 | 13504 | 600 | 13504 | 2.5% | 0.45866 | 8.25 | 0.19
Get Saved Scan Class4to8 | 40 | 7747 | 7530 | 14106 | 15246 | 16398 | 505 | 16398 | 0% | 0.49537 | 129.28 | 0.21
ITERATION 04/03/2023 Local server Results AFTER Index changes -- 40 USERS(index_branch_SS-184) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes | Percentage change for 40 users
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) Indexing done to below API calls School Login Fetch student and exam Get Roi Get brand Default brand | Rendering | Memory CPU |  | Thread Group:School Login | 95%
School Login | 40 | 180 | 142 | 370 | 422 | 466 | 44 | 466 | 0% | 18.2149 | 27.94 | 7.09 | Performance test executed with below load a. Users logged in: 40, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 d. Total Save marks API calls:80 e. Students record saved per iteration:100 f. Total students record saved:4000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000 |  |  |  |  | Thread Group:Fetch student and exam | 41%
Fetch student and exam | 40 | 16383 | 18610 | 26605 | 27932 | 32593 | 1632 | 32593 | 0% | 1.174 | 8.6 | 0.62 | [5 empty] | Thread Group:Get Roi | 62%
Get Roi | 40 | 3241 | 3127 | 5698 | 7538 | 7866 | 375 | 7866 | 0% | 0.99728 | 42.72 | 0.37 | [5 empty] | Thread Group:Get brand | 74%
Get brand | 40 | 2447 | 2229 | 4877 | 5042 | 6085 | 114 | 6085 | 0% | 0.92904 | 11.59 | 0.34 | [5 empty] | Thread Group:Default brand | 72%
Default brand | 40 | 804 | 731 | 1479 | 1815 | 1997 | 58 | 1997 | 0% | 0.91376 | 11.23 | 0.34
Save marks Class1to3 | 40 | 3109 | 3188 | 4736 | 5018 | 6366 | 814 | 6366 | 0% | 0.87329 | 108.77 | 168.38
Save marks Class4to8 | 40 | 3588 | 3379 | 5107 | 5597 | 6545 | 1555 | 6545 | 0% | 0.85936 | 1103.81 | 1236.66
Get Saved Scan Class1to3 | 40 | 1948 | 1712 | 3479 | 3734 | 4691 | 88 | 4691 | 0% | 0.89105 | 17.17 | 0.38
Get Saved Scan Class4to8 | 40 | 1861 | 1629 | 3529 | 4024 | 4594 | 33 | 4594 | 0% | 0.90092 | 196.53 | 0.39
ITERATION 04/03/2023 Local server Results BEFORE Index changes -- 50 USERS(v1_develop branch) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) |  | Rendering | Memory CPU
School Login | 50 | 3457 | 3649 | 5295 | 5391 | 5613 | 533 | 5613 | 0% | 6.7797 | 9.16 | 2.64 | Performance test executed with below load a. Users logged in: 50, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 d. Total Save marks API calls:100 e. Students record saved per iteration:100 f. Total students record saved:5000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000
Fetch student and exam | 50 | 23097 | 17596 | 51433 | 55074 | 93984 | 12374 | 93984 | 0% | 0.49615 | 4 | 0.26
Get Roi | 50 | 8476 | 3571 | 21354 | 22245 | 28024 | 302 | 28024 | 0% | 0.55147 | 23.63 | 0.2
Get brand | 50 | 9876 | 8743 | 19284 | 20449 | 25286 | 336 | 25286 | 0% | 0.53514 | 6.58 | 0.2
Default brand | 50 | 3293 | 3141 | 5734 | 6103 | 7115 | 83 | 7115 | 0% | 0.53632 | 6.59 | 0.2
Save marks Class1to3 | 50 | 12351 | 13593 | 18827 | 19713 | 20715 | 671 | 20715 | 0% | 0.53296 | 52.21 | 102.77
Save marks Class4to8 | 50 | 14876 | 15507 | 22262 | 23533 | 27473 | 1253 | 27473 | 0% | 0.54499 | 654.17 | 784.27
Get Saved Scan Class1to3 | 50 | 8370 | 9131 | 12260 | 13574 | 14625 | 82 | 14625 | 0% | 0.60698 | 12.53 | 0.26
Get Saved Scan Class4to8 | 50 | 7530 | 8202 | 12590 | 13507 | 16552 | 79 | 16552 | 0% | 0.68965 | 104.33 | 0.3
ITERATION 04/03/2023 Local server Results AFTER Index changes -- 50 USERS(index_branch_SS-184) | [12 empty] | Performance test host details | BackEnd Changes | FrontEnd Changes | Hardware changes | Other changes | Percentage change for 50 users
Transaction Name | # Samples | Average | Median | 90% Line | 95% Line | 99% Line | Min | Max | Error % | Throughput | Received KB/sec | Sent KB/sec | Local (4 Cores, 16 GB RAM, OS=Windows) | DataBase: Apurva's Index changes(https://github.com/Sunbird-Saral/Project-Saral/pull/364) Indexing done to below API calls School Login Fetch student and exam Get Roi Get brand Default brand | Rendering | Memory CPU |  | Thread Group:School Login | 37%
School Login | 50 | 2149 | 2296 | 2806 | 2870 | 2948 | 372 | 2948 | 0% | 12.1566 | 18.21 | 4.73 | Performance test executed with below load a. Users logged in: 50, b. Iterations per user: 01 c. Save Marks API calls per iteration:02 d. Total Save marks API calls:100 e. Students record saved per iteration:100 f. Total students record saved:5000 Mongo DB collections during test Schools: 20,000, Users: 1,00,000 Students: 8,00,000, Classes: 1,60,000 |  |  |  |  | Thread Group:Fetch student and exam | 60%
Fetch student and exam | 50 | 9452 | 6268 | 17885 | 24545 | 36424 | 3000 | 36424 | 0% | 1.2906 | 9.13 | 0.68 | [5 empty] | Thread Group:Get Roi | 29%
Get Roi | 50 | 5971 | 5954 | 11296 | 12299 | 14533 | 376 | 14533 | 0% | 1.1143 | 47.74 | 0.41 | [5 empty] | Thread Group:Get brand | 50%
Get brand | 50 | 4937 | 4944 | 8586 | 8719 | 9250 | 248 | 9250 | 0% | 1.0246 | 12.79 | 0.38 | [5 empty] | Thread Group:Default brand | 44%
Default brand | 50 | 1836 | 1870 | 2938 | 3113 | 4030 | 67 | 4030 | 0% | 1.0087 | 12.4 | 0.38
Save marks Class1to3 | 50 | 7140 | 7802 | 9884 | 10356 | 11414 | 1484 | 11414 | 0% | 0.98126 | 93.36 | 189.2
Save marks Class4to8 | 50 | 7851 | 7284 | 11745 | 12145 | 13017 | 1326 | 13017 | 0% | 1.0007 | 1201.6 | 1440.11
Get Saved Scan Class1to3 | 50 | 4182 | 4325 | 5972 | 6456 | 7139 | 129 | 7139 | 0% | 1.1203 | 33.17 | 0.48
Get Saved Scan Class4to8 | 50 | 3935 | 4334 | 6521 | 6528 | 6852 | 127 | 6852 | 0% | 1.2152 | 238.62 | 0.52

## Detailed Results
ITERATION 1 dd/mm 2023 Results
|  |  | Sl/no | Test Scenarios | Transaction Name | User Count
|  |  | 1 | School Login: (POST) | 01_App_Login
|  |  | 2 | Fetch student and exam (POST) | 02_Fetch_Exam
|  |  | 3 | Save marks (PUT) | 03_Save_All
|  |  | 4 | Get Saved Scan (POST) | 04_Get Saved Scan
System Details during Test Phase
HTTP Responses Summary
HTTP Responses | Total | Per Second
HTTP_200
HTTP_302
Performance Details
Maximum memory Utilization- 81%(3.10GB of 4GB)
Average Response Time
[5 empty] | Measurement | Minimum | Average | Maximum
Total Transaction
Maximum CPU Utilization- 45%
Transactions RT'!A2

## Transactions RT
Release 1
Test 1 - X number of AS with Y number of server nodes - X GB Heap
Transaction Name | Minimum | Average | Maximum | Std. Deviation | 90 Percent | Pass | Fail | Stop
Login_Transaction
Action_Transaction
Logout_Transaction

## DB SQL Stats
Saral App Release 1 Performance test
Test 1 - 4 AS with 2 server nodes
| Prepare | [6 empty] | Execute Update | [5 empty] | Execute Batch
SQL Statement 4013) | Overall Time [ms] | Stmt Pool Refs | Count | Pooled | Total Time [ms] | Avg Time [ms] | Max Time [ms] | Count | Total Time [ms] | Avg Time [ms] | Max Time [ms] | Rows Mod | Avg Rows Mod | Count | Total Time [ms] | Avg Time [ms] | Max Time [ms] | Rows Batched | Avg Rows Batched

## DB Table Stats
Amdeus OTC | R10

## Action ItemsOpen points
S.No | Action Description | Owner | Status | Comments